## Read me
Computational Research Notebook: development stages and test gates
Version | 0.1, 15 September 2026. Companion to Research_Notebook_Specification.docx and AGENTS.md.
Purpose | Breaks implementation into eight stages. Each stage lists the tasks to build and the gate tests that must pass before the next stage starts.
Gate rule | A stage is complete only when every task is Done and every gate test is Pass. Tests marked Both must pass on Windows and macOS. The Stage overview sheet calculates this automatically.
How to use | 1. Work through Tasks for the current stage in step order. 2. Record Status, Completed on and Notes (for example the pull request link) as you go. 3. Run each gate test for the stage and record Result, Date and Evidence. 4. Check Stage overview: start the next stage only when Can start shows Yes.
Cells you edit | Only the columns with orange headers and pale yellow cells: Tasks (Status, Completed on, Notes) and Test gates (Result, Date, Evidence, Notes). All other columns are reference data or formulas.
Task Status values | Not started, In progress, Done, Blocked
Test Result values | Not run, Pass, Fail
Example entry | Task S2-T04 "Implement nb-fs safe writes and path validation": Status = Done; Completed on = 2026-11-03; Notes = PR #41, reviewed by maintainer.
Example entry | Test S2-G05 "Atomic write survives crash": Result = Pass; Date = 2026-11-04; Evidence = link to CI run; Notes = passed on windows-latest and macos-latest.
Human review | Tasks marked Yes in Human review touch data safety, format, security or CI rules. AI may implement them, but the maintainer reviews the diff before merging.
Commands | Commands in Test gates refer to scripts defined in the starter kit package.json and CI workflows. They become runnable during Stage 0.
Changing gates | If a gate test is wrong or impossible, change it through an ADR and update this workbook in the same pull request. Do not mark a test Pass that was not run.

## Stage overview
Stage | Name | Goal | Est. weeks | Entry requirement | Tasks | Tasks done | Gate tests | Tests passed | Tests failed | Progress | Gate status | Can start
0 | Repository foundation | Set up the monorepo, agent rules, CI on Windows and macOS, and the checks that keep AI-generated code clean before any feature code exists. | 1 | Specification v0.1 approved | 13 | 0 | 9 | 0 | 0 | 0% | Not started | Yes
1 | Technical spikes | Prove the risky technologies work together before committing to them: Markdown round-trip, citations, Zotero, previews, PDF/A and the table. | 2 | Stage 0 gate passed | 11 | 0 | 9 | 0 | 0 | 0% | Not started | No: stage 0 gate open
2 | File format and index | Build the plain-file project format, safe writing, locking, history and the disposable index, plus questions, experiments, the table and the expanded view. | 5 | Stage 1 gate passed; spike ADRs merged | 13 | 0 | 15 | 0 | 0 | 0% | Not started | No: stage 1 gate open
3 | Evidence, groups and previews | Capture and version evidence, link large files, import from the inbox and VS Code, organise groups and preview artefacts. | 4 | Stage 2 gate passed | 11 | 0 | 13 | 0 | 0 | 0% | Not started | No: stage 2 gate open
4 | Writing and references | Rich-text sections with version-pinned artefact references, version updates, search and reverse lookups. Ends with an internal alpha. | 3 | Stage 3 gate passed | 12 | 0 | 13 | 0 | 0 | 0% | Not started | No: stage 3 gate open
5 | Citations and Literature | Zotero picker, bibliography cache, per-experiment citation contexts, styles and source repair. | 3 | Stage 4 gate passed | 9 | 0 | 8 | 0 | 0 | 0% | Not started | No: stage 4 gate open
6 | Archive and export | Integrity checks, manifest and verification, HTML and PDF/A exports, bundles and archived mode. | 2 | Stage 5 gate passed | 10 | 0 | 8 | 0 | 0 | 0% | Not started | No: stage 5 gate open
7 | Cross-platform release | Handoff and end-to-end suites on both platforms, build channels, signing, accessibility and performance sign-off. | 3 | Stage 6 gate passed | 10 | 0 | 10 | 0 | 0 | 0% | Not started | No: stage 6 gate open
| Total |  | 23 |  | 89 | 0 | 85 | 0 | 0 | 0%

## Tasks
Task ID | Stage | Step | Task | Definition of done | Spec reference | Human review | Status | Completed on | Notes / PR link
S0-T01 | 0 | 1 | Create the monorepo | pnpm workspaces and a Cargo workspace with the layout in spec 6.2; empty packages build. | 6.2 | No | Complete
S0-T02 | 0 | 2 | Add agent rules and project documents | AGENTS.md, CLAUDE.md, LICENSE (AGPL-3.0-or-later), README, CONTRIBUTING and the PR template committed from the starter kit. | 12, AGENTS.md | Yes | Complete
S0-T03 | 0 | 3 | Record initial ADRs | ADR-0001 to ADR-0008 from spec 15.1 written using the ADR template. | 15.1 | Yes | Complete
S0-T04 | 0 | 4 | Configure TypeScript checks | tsconfig with strict mode and noUncheckedIndexedAccess; ESLint with typescript-eslint; Prettier; `pnpm lint`, `pnpm typecheck` and `pnpm format:check` pass. | 12.1 | No | Complete
S0-T05 | 0 | 5 | Configure architecture boundaries | dependency-cruiser rules from the starter kit enforce spec 6.3 (for example UI cannot import Tauri fs APIs; format package has no I/O). | 6.3 | Yes | Complete
S0-T06 | 0 | 6 | Configure Rust checks | rustfmt, clippy with warnings denied, and cargo-deny with deny.toml from the starter kit. | 12.1 | No | Complete
S0-T07 | 0 | 7 | Configure npm licence allow-list | `pnpm licences:check` fails on any licence outside the allow-list. | 6.1 | Yes | Complete
S0-T08 | 0 | 8 | Set up test runners | Vitest projects (unit, property, golden, fixtures) and cargo test run with an example test in each; fast-check and proptest installed. | 12.1 | No | Complete
S0-T09 | 0 | 9 | Create CI and nightly workflows | ci.yml runs on windows-latest and macos-latest; nightly.yml scheduled; branch protection requires CI checks. | 12.2 | Yes | Complete
S0-T10 | 0 | 10 | Install pre-commit hooks | lefthook runs formatting, lint and typecheck on staged files. | 12.1 | No | Complete
S0-T11 | 0 | 11 | Create fixture harness | fixtures/projects/format-v1/ exists; a fixture test enumerates every fixture folder and fails if none are found. | 12.3 | No | Complete
S0-T12 | 0 | 12 | Minimal Tauri window | Tauri app with locked-down capabilities (no fs, shell or http plugins in the webview) launches on both platforms. | 6.7 | Yes | Complete
S0-T13 | 0 | 13 | Configure CODEOWNERS for protected paths | Changes to capabilities, migrations, nb-fs, format schemas and CI require maintainer review. | AGENTS.md | Yes | Complete
S1-T01 | 1 | 1 | Spike: Tiptap custom nodes with Markdown | artefactRef and citation nodes parse from and serialise to the syntax in spec 5.6 and 5.7 using @tiptap/markdown's MarkdownManager outside the editor. | 5.6, 5.7 | Yes | Complete
S1-T02 | 1 | 2 | Spike: round-trip property harness | fast-check arbitraries generate documents with all supported nodes, references and citations. | 12.1 | Yes | Complete
S1-T03 | 1 | 3 | Spike: citeproc-js in a Web Worker | Worker processes a context for numeric and author-date styles and returns clusters and bibliography after inserts and deletions. | 7.8 | No | Complete
S1-T04 | 1 | 4 | Spike: Zotero local API client in Rust | Detects not running, disabled (403) and connected; searches items; fetches CSL-JSON; records Zotero-Server-ID when present. | 7.8 | No | Complete
S1-T05 | 1 | 5 | Spike: previews on both platforms | Rust thumbnail for PNG and JPEG, pdf.js first page for PDF, SVG through img, shown in the Tauri window on Windows and macOS. | 8 | No | Complete
S1-T06 | 1 | 6 | Spike: Typst PDF/A from JSON | Embedded Typst renders one experiment JSON with a PDF figure to PDF/A-2b; user text passed only as data. | 7.12 | Yes | Complete
S1-T07 | 1 | 7 | Spike: TanStack table prototype | 500 generated experiments with question header rows, read-only rich summaries and virtualisation. | 7.3 | No | Complete
S1-T08 | 1 | 8 | Spike: YAML serialisation | `yaml` library writes double-quoted strings in documented key order and preserves unknown keys. | 5.2 | No | Complete
S1-T09 | 1 | 9 | Spike: git provenance | gix reads HEAD commit and file and tree dirty state; decide gix or git CLI. | 7.4 | No | Complete
S1-T10 | 1 | 10 | Define reference machine | Hardware for performance thresholds recorded in an ADR. | 10.1 | Yes | Complete
S1-T11 | 1 | 11 | Write spike ADRs and update the specification | One ADR per spike outcome; spec updated wherever a result differs. | 15 | Yes | Complete
S2-T01 | 2 | 1 | Write the normative format document and schemas | docs/format/format-v1.md and Zod schemas for every file; JSON Schemas exported to docs/format/schemas. | 5 | Yes | Complete
S2-T02 | 2 | 2 | Implement format parsing and serialising | packages/format parses and canonically serialises project.yaml, question files, experiment.md, artefacts.yaml and request.json. | 5.3-5.10 | Yes | Complete
S2-T03 | 2 | 3 | Preserve unknown content | Unknown frontmatter keys, preamble, unknown sections and passthrough blocks survive edits. | 5.5 | Yes | Complete
S2-T04 | 2 | 4 | Implement nb-fs safe writes and path validation | Atomic write with flush and rename, Windows retry, NFC and forward-slash normalisation, traversal rejection, writes restricted to _notebook. | 6.5, 9.3 | Yes | Complete
S2-T05 | 2 | 5 | Create, open and locate projects | Create layout and hygiene files, open by folder, recent projects in settings, locate moved projects, external root mapping per machine. | 7.1 | No | Complete
S2-T06 | 2 | 6 | Implement lock and read-only modes | Lock with heartbeat, stale takeover, banners for every read-only reason. | 5.11, 7.1 | Yes | Complete
S2-T07 | 2 | 7 | Implement the index | nb-index in the cache directory: schema, full rebuild, incremental update keyed by file size, time and hash; FTS5 table created. | 6.6 | No | Complete
S2-T08 | 2 | 8 | Implement watcher and conflicts | External changes reload; unsaved local edits plus external change keep both versions and open the conflict view. | 7.11 | Yes | Complete
S2-T09 | 2 | 9 | Implement history, trash and version-change backups | Snapshots before overwrite with retention policy; trash for deletions; backup before first write by a new app version. | 5.11, 7.11 | Yes | Complete
S2-T10 | 2 | 10 | Implement questions and experiments | Create, edit, move, delete to trash; ULIDs; ref allocation without reuse; duplicate ref detection. | 7.2 | No | Complete
S2-T11 | 2 | 11 | Build the workspace table | Question header rows, ordering from project.yaml, sort and filter within questions, column settings persisted, virtualised rows. | 7.3 | No | Complete
S2-T12 | 2 | 12 | Build the expanded experiment view | Section editors (plain Markdown without references yet), side-by-side Results Notes and Interpretation, autosave with status indicator. | 7.3, 7.7 | No | Complete
S2-T13 | 2 | 13 | Create fixture projects | minimal, typical, large (generated by committed script), edge-cases and malformed fixtures under format-v1. | 12.3 | Yes | Complete
S3-T01 | 3 | 1 | Implement copy capture | Hash while copying to temporary file, verify, atomic placement, Windows-safe names, collision suffixes, version naming, dedupe. | 7.4 | Yes | Complete
S3-T02 | 3 | 2 | Implement link mode and relink | Threshold and override; link records; availability checks; unavailable state; relink with ranked candidates requiring confirmation. | 7.4 | No | Complete
S3-T03 | 3 | 3 | Implement update from source | Detect changed source hash and offer a new version; never automatic. | FR-EVD-06 | No | Complete
S3-T04 | 3 | 4 | Record git provenance on capture | Repository path, commit, file and tree dirty flags stored with each version. | FR-EVD-12 | No | Complete
S3-T05 | 3 | 5 | Implement inbox import | Validate requests, create artefacts or versions, move payloads, remove processed requests, list invalid requests with errors. | 5.10 | Yes | Complete
S3-T06 | 3 | 6 | Build the VS Code extension | Add file to experiment command, project discovery, experiment quick pick via packages/format, role and mode options, atomic request writing with provenance. | 7.10 | Yes | Complete
S3-T07 | 3 | 7 | Implement discovery | Folder scan with include and exclude globs and platform clutter excludes, cancellable with progress, marks captured sources. | FR-EVD-09 | No | Complete
S3-T08 | 3 | 8 | Build the groups tree | Create, rename, nest, delete; Move to and Add to as separate actions by drag, keyboard and menu; ordering; Ungrouped area; large groups collapsed. | 7.5 | No | Complete
S3-T09 | 3 | 9 | Implement thumbnail cache | Cache directory keyed by content hash and size; bounded cache size. | FR-PRV-04 | No | Complete
S3-T10 | 3 | 10 | Implement previews | Image, PDF, SVG, delimited tables including gzip, text and scripts, notebooks, HTML (external only) and fallback, all bounded. | 8 | Yes | Complete
S3-T11 | 3 | 11 | Build the preview panel | Metadata, versions, groups, availability, provenance and open, reveal, VS Code, copy path and open project actions. | 7.6 | No | Complete
S4-T01 | 4 | 1 | Wire section editors to the format package | Methods, Results Notes and Interpretation load and save through packages/format with one live editor at a time. | 7.7 | No | Complete
S4-T02 | 4 | 2 | Implement @ autocomplete | Trigger rules, search by display name and filename, icons, group path, version, keyboard navigation, Escape, ARIA combobox. | FR-EDT-04 | No | Complete
S4-T03 | 4 | 3 | Implement reference chips | Current label, filename and version on hover or focus, activation opens pinned version preview. | FR-EDT-06 | No | Complete
S4-T04 | 4 | 4 | Implement newer-version updates | Indicators, Update reference, Update all in section. | FR-EDT-07 | No | Complete
S4-T05 | 4 | 5 | Handle detached references | References to removed artefacts render detached with the last label and are preserved on save. | FR-EDT-08 | No | Complete
S4-T06 | 4 | 6 | Rewrite labels and targets on save | All references match current metadata after every write. | FR-EDT-09 | Yes | Complete
S4-T07 | 4 | 7 | Render read-only table summaries | Cells render Markdown summaries with chips as static elements, no editor instances. | FR-TBL-05 | No | Complete
S4-T08 | 4 | 8 | Implement search | FTS5 search across sections, titles, display names and filenames; grouped results opening at the location. | 7.9 | No | Complete
S4-T09 | 4 | 9 | Implement Referenced in lookup | Artefact panel lists every reference with experiment and section. | FR-SRC-03 | No | Complete
S4-T10 | 4 | 10 | Run internal alpha | Maintainer records one real experiment end to end on a copy of a real project and files issues. | 13 | Yes | Not started
S4-T11 | 4 | 11 | Edit in the table | Methods, Results Notes, Interpretation, title and status edit in place in the table; the edited row grows and stays rendered; one live editor across table and expanded view, saving before switching; keyboard grid navigation; section columns fill spare width. | FR-TBL-05, FR-TBL-11, FR-TBL-12, FR-EDT-03 | Yes | Complete |  | ADR-0043 supersedes ADR-0005.
S4-T12 | 4 | 12 | Wire evidence into the table | Files are added to an experiment by picker, drag-and-drop, discovery and VS Code inbox (imported on open), copied or linked, and organised in the Results cell as folders; missing linked files can be relinked after confirmation; artefacts.yaml is loaded and written with the rest of the notebook; the preview spike is removed. | FR-TBL-06, FR-EVD-01, FR-EVD-02, FR-EVD-05, FR-EVD-08, FR-EVD-09, FR-GRP-01 to FR-GRP-06, 5.10 | Yes | Not started |  | ADR-0044. Issue #50.
S5-T01 | 5 | 1 | Integrate Zotero status and onboarding | Status indicator and guidance for enabling the local API. | FR-CIT-01 | No | Not started
S5-T02 | 5 | 2 | Build the citation picker | Slash menu Cite item, debounced search, multi-select, locator, prefix and suffix, keyboard operable. | FR-CIT-03 | No | Not started
S5-T03 | 5 | 3 | Serialise citation nodes | Pandoc citation syntax with citekey grammar; hand-written forms preserved. | 5.7 | Yes | Not started
S5-T04 | 5 | 4 | Maintain bibliography.json | Insert adds CSL-JSON; refresh action; ok, trashed and missing states; server ID mismatch prompt. | 5.9, FR-CIT-07 | Yes | Not started
S5-T05 | 5 | 5 | Implement citation contexts and Literature block | Per experiment, Methods then Interpretation; one entry per source; numbering by first appearance; block regenerated and written to file with change warning. | FR-CIT-09, FR-CIT-10 | Yes | Not started
S5-T06 | 5 | 6 | Implement style management | Bundled in-text styles, import .csl, reject note styles, copy active style to styles/. | FR-CIT-11 | No | Not started
S5-T07 | 5 | 7 | Build source details panel | Metadata, Open in Zotero, DOI, Open PDF when available. | FR-CIT-04 | No | Not started
S5-T08 | 5 | 8 | Implement source repair | Replace a missing or trashed source with another item, updating citekeys in text. | FR-CIT-08 | Yes | Not started
S5-T09 | 5 | 9 | Implement Cited by lookup | List experiments citing a source. | FR-CIT-12 | No | Not started
S6-T01 | 6 | 1 | Build the integrity check | Report of missing files, unresolved references, external files and source problems, each resolvable or acknowledgeable. | FR-ARC-01 | No | Not started
S6-T02 | 6 | 2 | Generate the manifest | manifest.csv with path, size, time, SHA-256, experiments and groups. | FR-ARC-02 | No | Not started
S6-T03 | 6 | 3 | Implement Verify | Re-hash files against the manifest and report differences. | FR-ARC-03 | Yes | Not started
S6-T04 | 6 | 4 | Implement git bundle option | git bundle for each repository referenced by provenance. | FR-ARC-04 | No | Not started
S6-T05 | 6 | 5 | Build HTML export | Static pages per question and experiment, downscaled figures, sampled tables, relative links to originals. | FR-ARC-05 | No | Not started
S6-T06 | 6 | 6 | Build PDF/A-3 export | Typst template over notebook.json with embedded notebook.json and bibliography.json, combined project bibliography as a fresh context. | FR-ARC-06 | Yes | Not started
S6-T07 | 6 | 7 | Build machine-readable export | notebook.json, JSON Schemas and Markdown renderings. | FR-ARC-07 | No | Not started
S6-T08 | 6 | 8 | Build bundles | Notebook bundle and full archive as ZIP64, stored mode for compressed formats, FAT32 warning, registered extension. | FR-ARC-08 | Yes | Not started
S6-T09 | 6 | 9 | Implement archived mode and unarchive | Archived flag, read-only opening, unarchive with backup and migration. | FR-ARC-09, FR-ARC-10 | Yes | Not started
S6-T10 | 6 | 10 | Generate README with recovery instructions | _notebook/README.md explains the folder and includes the Pandoc command. | A.3 | No | Not started
S7-T01 | 7 | 1 | Build the cross-OS handoff jobs | Nightly jobs create and edit a project on Windows, verify and edit on macOS, and the reverse. | 12.2 | Yes | Not started
S7-T02 | 7 | 2 | Build the end-to-end suite | WebdriverIO with the Tauri service covering create, capture, group, reference, cite, archive on both platforms. | 12.1 | No | Not started
S7-T03 | 7 | 3 | Separate stable and development builds | Different application identifiers and settings; development build read-only on projects not marked as test copies. | ADR-0008 | Yes | Not started
S7-T04 | 7 | 4 | Sign and notarise macOS builds | Universal build signed and notarised in the release workflow. | 9.4 | Yes | Not started
S7-T05 | 7 | 5 | Sign Windows builds | Signed installer produced in the release workflow. | 9.4 | Yes | Not started
S7-T06 | 7 | 6 | Add opt-in updater | Signature-verified updates, off by default, version-change backup on first write. | FR-HIS-04 | Yes | Not started
S7-T07 | 7 | 7 | Accessibility pass | Keyboard, focus, contrast and screen reader fixes; axe-core clean. | 10.2 | No | Not started
S7-T08 | 7 | 8 | Performance pass | All section 10.1 thresholds met and recorded. | 10.1 | No | Not started
S7-T09 | 7 | 9 | Register bundle file association | Double-clicking a bundle opens the application on both platforms. | FR-PRJ-02 | No | Not started
S7-T10 | 7 | 10 | Publish user and format documentation | User guide, format-v1 documentation and recovery guide published with the release. | 5, A.3 | Yes | Not started

## Test gates
Test ID | Stage | Gate test | Type | How to run | Pass criterion | Platforms | Automated in CI | CI trigger | Result | Date | Evidence / link | Notes
S0-G01 | 0 | CI runs green on both platforms | Static | Open a PR with no changes; watch ci.yml | All jobs succeed on windows-latest and macos-latest | Both | Yes | Pull request | Not run
S0-G02 | 0 | Lint violation fails CI | Negative | Temporary PR adding an unused variable and `any` | CI fails at the lint step; PR closed afterwards | Both | Yes | Pull request | Not run
S0-G03 | 0 | Failing test fails CI | Negative | Temporary PR with `expect(1).toBe(2)` and a failing Rust test | CI fails in both test steps | Both | Yes | Pull request | Not run
S0-G04 | 0 | Disallowed licence fails CI | Negative | Temporary PR adding a dependency with a licence outside the allow-list | `cargo deny check` or `pnpm licences:check` fails | Both | Yes | Pull request | Not run
S0-G05 | 0 | Boundary violation fails CI | Negative | Temporary PR importing `@tauri-apps/plugin-fs` in apps/desktop/src | `pnpm deps:check` fails with the named rule | Both | Yes | Pull request | Not run
S0-G06 | 0 | Pre-commit hook blocks unformatted code | Manual | Commit a badly formatted file locally | Commit rejected with a formatting message | Both | No | Local | Not run
S0-G07 | 0 | Tauri window launches | Manual | `pnpm --filter desktop tauri dev` on each platform | Window opens with no console errors | Both | No | Manual | Not run
S0-G08 | 0 | Webview has no filesystem, shell or http permissions | Static | `pnpm test:unit -- capabilities` (test parses capability JSON) | Test fails if any forbidden permission is present | Both | Yes | Pull request | Not run
S0-G09 | 0 | Fixture harness detects missing fixtures | Negative | Run `pnpm test:fixtures` with the fixture folder empty | Harness fails with a clear message | Both | Yes | Pull request | Not run
S1-G01 | 1 | Round-trip property: generated documents | Property | `pnpm test:property -- roundtrip` with FC_NUM_RUNS=10000 | parse(serialise(doc)) deep-equals doc for every case | Both | Yes | Pull request (1,000) and nightly | Not run
S1-G02 | 1 | Round-trip golden: edge-case corpus | Golden | `pnpm test:golden -- markdown-corpus` | Nested lists, code blocks containing @ and [@...], titled links and raw HTML byte-identical after serialise(parse()) | Both | Yes | Pull request | Not run
S1-G03 | 1 | Citation numbering property | Property | `pnpm test:property -- citation-context` | After random insert, delete and move sequences, numbers follow first appearance and each source has one entry | Both | Yes | Pull request | Not run
S1-G04 | 1 | Zotero client status handling | Integration | `cargo test -p nb-zotero` against the mock server; manual run against current Zotero release and beta | Not running, 403 and connected states reported correctly; CSL-JSON parsed | Both | Partly | Pull request and manual | Not run
S1-G05 | 1 | Previews render on both platforms | Manual | Open spike preview window with sample PNG, PDF and SVG | All three visible and correctly scaled on Windows and macOS; screenshots attached | Both | No | Manual | Not run
S1-G06 | 1 | Typst output is valid PDF/A-2b | Golden | Nightly veraPDF step on spike output | veraPDF reports compliant | Both | Yes | Nightly | Not run
S1-G07 | 1 | Typst treats user text as data | Security | `cargo test -p nb-export -- injection` | Notes containing #, $, and Typst function calls render literally | Both | Yes | Pull request | Not run
S1-G08 | 1 | Table prototype scroll performance | Performance | Profile scrolling 500 rows in the webview devtools on each platform | No frame longer than 50 ms | Both | No | Manual | Not run
S1-G09 | 1 | Spike review | Manual | Maintainer reviews spike ADRs | Every spike passed or has an approved alternative ADR | N/A | No | Manual | Not run
S2-G01 | 2 | Canonical serialisation of fixtures | Golden | `pnpm test:fixtures` | serialise(parse(file)) is byte-identical for every file in every fixture | Both | Yes | Pull request | Not run
S2-G02 | 2 | Model round-trip property | Property | `pnpm test:property -- project-model` | Generated projects serialise and parse to deep-equal models | Both | Yes | Pull request and nightly | Not run
S2-G03 | 2 | Unknown content preserved | Integration | `pnpm test:unit -- preserve-unknown` using edge-cases fixture | Unknown keys, preamble, unknown sections and passthrough blocks unchanged after an edit and save | Both | Yes | Pull request | Not run
S2-G04 | 2 | Malformed files open read-only | Integration | `pnpm test:fixtures -- malformed` | Read-only mode reported; file hashes unchanged after opening, editing attempts and closing | Both | Yes | Pull request | Not run
S2-G05 | 2 | Atomic write survives crash | Fault injection | `cargo test -p nb-fs --test atomic_write` | Killing the writer at random points leaves the old or new complete file, never partial | Both | Yes | Pull request | Not run
S2-G06 | 2 | Nothing outside _notebook changes | Filesystem safety | `pnpm test:fs-safety` | Directory snapshot of the project root outside _notebook identical before and after the integration suite | Both | Yes | Pull request | Not run
S2-G07 | 2 | Index rebuild equality | Integration | `cargo test -p nb-index --test rebuild` | Normalised dump of a rebuilt index equals the incrementally maintained index | Both | Yes | Pull request | Not run
S2-G08 | 2 | External edit and conflict | Integration | `pnpm test:unit -- watcher-conflict` plus manual edit in VS Code | External edit reloads; concurrent unsaved edit produces conflict with both versions | Both | Partly | Pull request and manual | Not run
S2-G09 | 2 | Lock behaviour | Integration | `cargo test -p nb-fs --test lock` | Second instance read-only; stale lock takeover requires confirmation flag | Both | Yes | Pull request | Not run
S2-G10 | 2 | Newer format opens read-only | Integration | `pnpm test:fixtures -- future-format` | Project with format_version 2 opens read-only with banner reason | Both | Yes | Pull request | Not run
S2-G11 | 2 | Moved project resolves | Integration | `cargo test --test move_project` copying fixture to a new temporary path | All references and captured files resolve without repair | Both | Yes | Pull request | Not run
S2-G12 | 2 | History retention | Unit | `cargo test -p nb-fs -- history_retention` with mocked clock | Snapshot counts match policy at 1 day, 7 days, 90 days and beyond | Both | Yes | Pull request | Not run
S2-G13 | 2 | CRLF and BOM input | Unit | `pnpm test:unit -- encoding` | Files with CRLF and BOM parse; written files are LF without BOM | Both | Yes | Pull request | Not run
S2-G14 | 2 | Large project opens quickly | Performance | `pnpm bench -- open-large` | Table interactive in under 2 s with warm index; rebuild under 20 s | Both | Yes | Nightly | Not run
S2-G15 | 2 | Windows-created and macOS-created fixtures | Cross-platform | Nightly handoff job (early version) | Fixture created on each platform opens and saves canonically on the other | Both | Yes | Nightly | Not run
S3-G01 | 3 | Capture dedupe and versioning | Property | `pnpm test:property -- capture` and `cargo test -p nb-fs -- capture` | Same content creates no version; changed content creates v2; v1 bytes unchanged | Both | Yes | Pull request | Not run
S3-G02 | 3 | Group operations preserve data | Property | `pnpm test:property -- groups` | Random operation sequences keep every artefact ID, all file bytes and ordering; no duplicate item within a group | Both | Yes | Pull request | Not run
S3-G03 | 3 | Nothing outside _notebook changes during capture | Filesystem safety | `pnpm test:fs-safety` | Source files unchanged in bytes and modification time after capture, relink and discovery | Both | Yes | Pull request | Not run
S3-G04 | 3 | Inbox import while app closed | Integration | `cargo test -p nb-fs --test inbox_import` and `pnpm test:unit -- inbox-open` | Requests written with no app running import on next open; invalid requests stay with error | Both | Yes | Pull request | Not run
S3-G05 | 3 | VS Code extension writes valid requests | Integration | `pnpm test:vscode` | Request validates against schema; payload hash matches; provenance commit and dirty flags correct in a test repository | Both | Yes | Pull request | Not run
S3-G06 | 3 | Relink never auto-applies | Integration | `cargo test -p nb-fs -- relink` and `pnpm test:unit -- relink` | Candidates returned ranked; artefact unchanged until the person confirms a candidate (the UI calling `applyRelink`, ADR-0044) | Both | Yes | Pull request | Not run
S3-G07 | 3 | Discovery on 50,000 files | Performance | `cargo test -p nb-fs --test discovery_perf` (ADR-0035 §10) | Progress within 500 ms; cancel within 1 s; excluded folders not traversed | Both | Yes | Nightly | Not run
S3-G08 | 3 | Bounded table preview | Integration | `cargo test -p nb-preview -- bounds` | 2 GB CSV: read limits respected, memory increase under 50 MB; gzip works | Both | Yes | Pull request | Not run
S3-G09 | 3 | SVG scripts do not execute; HTML not rendered | Security | `pnpm test:e2e -- preview-security` | Script-bearing SVG triggers no script; HTML artefact offers only external open | Both | Yes | Nightly | Not run
S3-G10 | 3 | Windows-safe filenames | Property | `cargo test -p nb-fs -- filename_sanitise` (proptest) | Generated names are valid on Windows, NFC, at most 64 characters, and unique after case folding | Both | Yes | Pull request | Not run
S3-G11 | 3 | Large Results tree performance | Performance | `pnpm bench -- results-tree` | 2,000 artefacts render collapsed in under 200 ms | Both | Yes | Nightly | Not run
S3-G12 | 3 | Keyboard-only group operations | Accessibility | Manual test and `pnpm test:a11y` | Create, move and add memberships without a mouse; no serious axe violations | Both | Partly | Pull request and manual | Not run
S3-G13 | 3 | Previews on both platforms | Manual | Open typical fixture previews on Windows and macOS | All preview types render or show fallback states; screenshots attached | Both | No | Manual | Not run
S4-G01 | 4 | Reference syntax written correctly | Golden | `pnpm test:golden -- references` | Inserted references match spec 5.6 exactly | Both | Yes | Pull request | Not run
S4-G02 | 4 | Files readable in other tools | Manual | Open typical fixture in VS Code preview and as an Obsidian vault | Links open the correct files; text readable | Both | No | Manual | Not run
S4-G03 | 4 | Rename updates references | Integration | `pnpm test:unit -- rename-artefact` | All labels updated in files; IDs and versions unchanged | Both | Yes | Pull request | Not run
S4-G04 | 4 | Round-trip with references | Property | `pnpm test:property -- roundtrip` | Extended arbitraries including references in all sections pass | Both | Yes | Pull request and nightly | Not run
S4-G05 | 4 | Autosave crash window | Fault injection | `pnpm test:e2e -- autosave-crash` | Killing the app 2 s after typing loses at most 1.5 s of input; file never partial | Both | Yes | Nightly | Not run
S4-G06 | 4 | Search speed and coverage | Performance | `pnpm bench -- search` | Results under 200 ms on large fixture; matches in every section type | Both | Yes | Nightly | Not run
S4-G07 | 4 | Referenced in is complete | Property | `pnpm test:property -- reverse-refs` | Lookup equals brute-force scan of all files | Both | Yes | Pull request | Not run
S4-G08 | 4 | Single live editor | Unit | `pnpm test:unit -- editor-instances` | At most one editor instance mounted at any time across the table and the expanded view | Both | Yes | Pull request | Not run
S4-G09 | 4 | Autocomplete accessibility | Accessibility | `pnpm test:a11y` plus NVDA on Windows and VoiceOver on macOS | Combobox announced and operable by keyboard | Both | Partly | Pull request and manual | Not run
S4-G10 | 4 | Internal alpha complete | Manual | Maintainer dogfood on a copy of a real project | One real experiment recorded end to end; blocking issues fixed | Both | No | Manual | Not run
S4-G11 | 4 | Inline edit saves | Unit | `pnpm test:unit -- inline-edit` | A section edited in a table cell writes the same file bytes as the same edit in the expanded view; switching cells saves pending text first | Both | Yes | Pull request | Not run |  |  | Added by ADR-0043.
S4-G12 | 4 | Scroll with an active editor | Performance | Profile scrolling the 500-experiment table in the webview devtools with one cell being edited, on each platform | No frame longer than 50 ms; the edited row stays rendered and keeps its text | Both | No | Manual | Not run |  |  | Added by ADR-0043.
S4-G13 | 4 | Evidence added in the table | Integration | `pnpm test:unit -- evidence-capture` and `pnpm test:fs-safety` | A picked or dropped file becomes a new artefact or version in artefacts.yaml; a duplicate makes no version; a file outside the project and external roots is refused; source files are unchanged | Both | Yes | Pull request | Not run |  |  | Added by ADR-0044.
S5-G01 | 5 | Literature consistency property | Property | `pnpm test:property -- literature` | Random citation edits keep Literature equal to cited sources, numbered by first appearance, one entry per source | Both | Yes | Pull request and nightly | Not run
S5-G02 | 5 | Style change does not alter text | Integration | `pnpm test:unit -- style-switch` | Section text hashes unchanged apart from the literature block | Both | Yes | Pull request | Not run
S5-G03 | 5 | Pandoc agrees with the app | Golden | `pnpm test:golden -- pandoc-citeproc` (CI installs Pandoc) | Normalised Pandoc bibliography text equals app Literature for fixtures | Both | Yes | Pull request | Not run
S5-G04 | 5 | Rendering with Zotero closed | Integration | `pnpm test:unit -- offline-citations` | Existing citations render from bibliography.json; picker shows offline state | Both | Yes | Pull request | Not run
S5-G05 | 5 | Server ID mismatch | Integration | `cargo test -p nb-zotero -- server_id` with mock | 412 and mismatched IDs prompt before overwrite; no data lost | Both | Yes | Pull request | Not run
S5-G06 | 5 | Trashed and missing sources | Integration | `pnpm test:unit -- source-repair` | States shown; replacement updates citekeys; citation text otherwise unchanged | Both | Yes | Pull request | Not run
S5-G07 | 5 | Zotero contract | Contract | `cargo test -p nb-zotero --test contract` on recorded responses; manual run against current Zotero release and beta | All contract cases pass | Both | Partly | Pull request and before release | Not run
S5-G08 | 5 | Note styles rejected | Unit | `pnpm test:unit -- style-validation` | Note-class CSL styles rejected with message | Both | Yes | Pull request | Not run
S6-G01 | 6 | PDF/A-3b validity | Golden | Nightly veraPDF step on typical fixture export | Compliant; embedded notebook.json and bibliography.json present | Both | Yes | Nightly | Not run
S6-G02 | 6 | Export golden files | Golden | `pnpm test:golden -- export` | notebook.json and HTML structure match golden files | Both | Yes | Pull request | Not run
S6-G03 | 6 | Verify detects corruption | Property | `cargo test -p nb-archive -- verify` | A single flipped byte in any file is reported | Both | Yes | Pull request | Not run
S6-G04 | 6 | ZIP64 full archive round-trip | Integration | `cargo test -p nb-archive --test zip64 -- --ignored` (nightly only) | Archive over 4 GB extracts byte-identical | Both | Yes | Nightly | Not run
S6-G05 | 6 | Notebook bundle without data | Integration | `cargo test -p nb-archive -- notebook_bundle` | Opens with files unavailable; pointing to data folder matches by checksum | Both | Yes | Pull request | Not run
S6-G06 | 6 | Archived projects are not written | Filesystem safety | `pnpm test:fs-safety -- archived` | No file under the project changes while archived project is open and used | Both | Yes | Pull request | Not run
S6-G07 | 6 | Pandoc recovery command works | Integration | CI runs the README command on the typical fixture | Pandoc exits 0 and output contains the bibliography | Both | Yes | Pull request | Not run
S6-G08 | 6 | Archive crosses platforms | Cross-platform | Nightly handoff job with archive step | Archive made on each platform verifies and opens read-only on the other | Both | Yes | Nightly | Not run
S7-G01 | 7 | Handoff both directions | Cross-platform | `nightly.yml` handoff jobs | Windows to macOS and macOS to Windows jobs green on three consecutive nights | Both | Yes | Nightly | Not run
S7-G02 | 7 | End-to-end core workflow | E2E | `pnpm test:e2e` | Create, capture, group, reference, cite, archive pass on both platforms | Both | Yes | Nightly and release | Not run
S7-G03 | 7 | Development build protection | Integration | `pnpm test:e2e -- dev-build-readonly` | Development build opens non-test project read-only | Both | Yes | Release | Not run
S7-G04 | 7 | Clean machine installers | Manual | Install on clean Windows 11 and macOS virtual machines | Launch without security overrides; uninstall leaves project files untouched | Both | No | Release | Not run
S7-G05 | 7 | Update creates backup | Integration | `pnpm test:e2e -- version-change-backup` | Backup exists before first write by new version | Both | Yes | Release | Not run
S7-G06 | 7 | Recovery without the application | Manual | Uninstall app; open project in text editor; run Pandoc command | All notes readable; experiment renders with citations | Both | No | Release | Not run
S7-G07 | 7 | Accessibility sign-off | Accessibility | `pnpm test:a11y`; keyboard-only and screen reader walkthrough | No serious or critical axe violations; walkthrough completed on both platforms | Both | Partly | Release | Not run
S7-G08 | 7 | Performance sign-off | Performance | `pnpm bench` | Every threshold in spec 10.1 met on reference machine | Both | Yes | Release | Not run
S7-G09 | 7 | Mutation score on critical modules | Mutation | `pnpm test:mutation` and `cargo mutants -p nb-fs` | Mutation score at least 80% for packages/format, packages/citations and nb-fs | Both | Yes | Weekly | Not run
S7-G10 | 7 | Acceptance criteria sign-off | Manual | Walk through spec section 13 | AC-01 to AC-20 all confirmed with evidence links | Both | No | Release | Not run

## Test suites
Suite | Layer | Tools | Location | Command | Trigger | Platforms | Required to merge | Introduced in stage
Formatting, linting and types | Static | Prettier, ESLint, tsc, rustfmt, clippy | Whole repository | pnpm check:static | Pre-commit and pull request | Both | Yes | 0
Architecture boundaries | Static | dependency-cruiser | apps, packages, extensions | pnpm deps:check | Pull request | Both | Yes | 0
Licences and advisories | Static | cargo-deny, npm licence checker, pnpm audit | Dependencies | cargo deny check && pnpm licences:check | Pull request and weekly | Both | Yes | 0
TypeScript unit and component | Unit | Vitest, Testing Library | packages/*, apps/desktop/src, extensions/vscode | pnpm test:unit | Pull request | Both | Yes | 0
Rust unit and integration | Unit / integration | cargo test | apps/desktop/src-tauri | pnpm test:rust | Pull request | Both | Yes | 0
Property tests (short) | Property | fast-check, proptest | packages/format, packages/citations, nb-fs | pnpm test:property | Pull request (1,000 cases) | Both | Yes | 1
Property tests (long) | Property | fast-check, proptest | Same as above | FC_NUM_RUNS=100000 PROPTEST_CASES=100000 pnpm test:property | Nightly | Both | No (nightly alert) | 1
Golden files | Golden | Vitest snapshot files | packages/format, nb-export | pnpm test:golden | Pull request | Both | Yes | 1
Fixture compatibility | Integration | Vitest | fixtures/projects | pnpm test:fixtures | Pull request | Both | Yes | 2
Filesystem safety | Integration | cargo test with directory snapshots | nb-fs and command integration tests | pnpm test:fs-safety | Pull request | Both | Yes | 2
Zotero contract | Contract | cargo test with recorded responses | nb-zotero | cargo test -p nb-zotero --test contract | Pull request | Both | Yes | 1
VS Code extension | Integration | @vscode/test-electron | extensions/vscode | pnpm test:vscode | Pull request | Both | Yes | 3
Accessibility | Accessibility | axe-core | apps/desktop | pnpm test:a11y | Pull request touching UI | Both | Yes | 3
End-to-end | E2E | WebdriverIO with Tauri service | apps/desktop/e2e | pnpm test:e2e | Nightly and release | Both | Release only | 4
Cross-OS handoff | Cross-platform | GitHub Actions artefacts | scripts/handoff | pnpm handoff:create / pnpm handoff:verify | Nightly and release | Windows and macOS jobs | Release only | 2
PDF/A validation | Golden | veraPDF | nb-export output | verapdf --flavour 3b exports/*.pdf | Nightly | Both | Release only | 1
Performance benchmarks | Performance | Vitest bench, criterion | packages, apps/desktop | pnpm bench | Nightly | Both | Release only | 2
Mutation testing | Mutation | StrykerJS, cargo-mutants | packages/format, packages/citations, nb-fs | pnpm test:mutation && cargo mutants -p nb-fs | Weekly | One platform | Release only | 2